## Work
Date | Start time | End time | Time spent | Work category | Work attempted | Work done | Test | Problems | Solution | Notes
2025-09-07 | 21:00 | 22:25 | 1:25 | Design | Information about the business that the website will be based on | Identity of a fictional coffee shop | Concept review
2025-09-12 | 15:00 | 18:00 | 3:00 | Design | Logo | Logo and image resources | Visual consistency check
2025-09-15 | 20:00 | 3:00 | -0.70833 | Design | Outline of the homepage content | Home page design with overview of each page of the website | Layout feasibility
2025-09-17 | 13:00 | 14:30 | 1:30 | Requirements Gathering | Resource to be used for the website such as images, videos, embeds, and other media. | Few of the photo resources | Image format compatibility | Slow internet connection |  | I made sure that all photos is in png format, all videos are in mp4 format, and all files are in pdf format.
2025-09-29 | 14:30 | 18:30 | 4:00 | Development | Social media pages & other external resources for the business. Also aiming to create most part of the landing page | Internal page for social pages | Link navigation test
2025-10-01 | 10:00 | 13:00 | 3:00 | Design | Wireframe design for all pages | Wireframe layout for the project to follow | Wireframe usability
2025-10-01 | 14:00 | 18:00 | 4:00 | Development | Navigation & footer components | Responsive and reusable navbar and footer with dark mode feature | Dark mode toggle functionality | Dark mode only changes the colors when turned on | When dark mode is toggled, it changes the source of the photo to be from the light mode folder to dark mode so even the photos changes
2025-10-02 | 10:00 | 12:00 | 2:00 | Development | Page templates & reusability | Javascript for reusability and components initialization | Component import verification
2025-10-03 | 14:00 | 16:00 | 2:00 | Development | Landing page layout | Homepage structure | Browser rendering test
2025-10-04 | 15:00 | 18:00 | 3:00 | Development | Landing page content | Hero section and featured areas | Content placement accuracy
2025-10-07 | 14:00 | 17:00 | 3:00 | Development | Landing page styling | CSS effects and responsive design | CSS animation performance
2025-10-08 | 16:00 | 18:00 | 2:00 | Development | Landing page components | Interactive elements and animations | Interaction responsiveness
2025-10-09 | 14:00 | 16:00 | 2:00 | Development | Landing page polish | Final touches and optimization | Page load speed
2025-10-10 | 15:00 | 18:00 | 3:00 | Development | Menu page development | Food and drink tables with Bootstrap | Table scrolling on mobile
2025-10-11 | 10:00 | 12:00 | 2:00 | Development | Branches page | Accordion layout for locations | Accordion expand/collapse
2025-10-14 | 14:00 | 18:00 | 4:00 | Development | Courses page | Course cards with pricing and details | Card hover and carousel functionaltiies
2025-10-15 | 15:00 | 17:00 | 2:00 | Development | Contact page layout | Form structure and styling | Form field focus states
2025-10-15 | 17:00 | 17:30 | 0:30 | Development | Contact form validation | Client-side validation implementation | Input validation messages
2025-10-16 | 14:00 | 16:00 | 2:00 | Development | About page content | Company story and team information | Text readability assessment
2025-10-16 | 16:00 | 19:00 | 3:00 | Development | Photobooth feature | Canvas-based photo capture functionality | Camera permission requests
2025-10-17 | 15:00 | 17:00 | 2:00 | Development | Photobooth completion | Final photobooth testing and styling | Photo capture quality | Photobooth on the phone won't work unless tilted | Make the user tilt their phone to use the photobooth | I made another frame for phones to use it, but camera object of devices have different sizes and ratio even when the ideal was set to 16/9 ratio so it wasn't used.
2025-11-10 | 8:00 | 14:30 | 6:30 | Testing | Website test on different devices | Various devices tested (Phone and Desktops). Tested Bootstrap breakpoints. | Cross-browser compatibility
2025-11-11 | 8:30 | 10:30 | 2:00 | Tweak and Fixes | Fix some parts and some inconsistencies that I and my testers can find | Refined code | Bug fix verification